VIETNAM INFRASTRUCTURE INTELLIGENCE HUB

Vietnam Environmental Industry Development Program

Decision No. 1894/QD-TTg | September 4, 2025

| Plan ID | VN-ENV-IND-1894 |
| --- | --- |
| Official Title | Program for the Development of Vietnam's Environmental Industry Sector 2025–2030 |
| Lead Ministry | Ministry of Industry and Trade (MOIT) |
| Signed By | Deputy PM Tran Hong Ha — September 4, 2025 |
| Report Articles | Matched: 448 ¦ Relevant: 38 ¦ Report (2026): 1 |

Generated: 2026-04-14 11:00  |  W16/2026  |  CONFIDENTIAL

# 1. What is Decision 1894?

⚠️ IMPORTANT DISTINCTION Decision 1894 is NOT a waste infrastructure construction plan. It is a NATIONAL INDUSTRIAL DEVELOPMENT PROGRAM to build up Vietnam's domestic environmental technology industry — i.e., developing Vietnamese-made technology, equipment, and services for environmental protection. This is distinct from: • VN-WW-2030 (wastewater treatment plant construction) • Solid Waste Infrastructure Plans (landfill/incinerator construction) • VN-ENV infrastructure programs D1894 focuses on WHO MAKES the technology, not WHO BUILDS the plants.

National Industrial Development Program — NOT a waste infrastructure construction plan. This is a TECHNOLOGY INDUSTRY BUILD-UP program focused on domestic production capability, R&D, market formation, and enterprise development in the environmental technology sector.

## Core Philosophy

▪ Develop Environmental Industry (CNMT) as an independent economic sector contributing to national GDP

▪ Private sector is the central force — strong support via green credit, tech access, market development

▪ Innovation, digital transformation, and modern technology as growth drivers

▪ Strategic self-reliance: domestic production to reduce import dependency on environmental technology

▪ Export ambition: Vietnam to export environmental technology/equipment where it gains competitive advantage

# 2. National KPI Targets — 2030

| Technology Sector | 2030 Target (Domestic Market Share) | Scope | Current Gap |
| --- | --- | --- | --- |
| Wastewater Treatment Technology | 70–80% of domestic demand + export | WWTP equipment, modules, chemicals | High import dependency (Korea, Japan, EU) |
| Exhaust Gas Treatment Technology | 60–70% of domestic demand | Air pollution control equipment | Advanced systems almost fully imported |
| Solid & Hazardous Waste Technology | 50–60% (collection/transport) 60–70% (sorting/recycling) | Collection vehicles, sorting lines, recycling machinery | Incineration/hazardous treatment relies on imports |
| Environmental Monitoring Equipment | 20% of domestic demand | IoT sensors, analyzers, AMS stations | Almost entirely import-dependent |
| Waste-to-Energy Technology | Domestic capability established | WTE boilers, biogas, RDF systems | Large-scale WTE uses Chinese/EU technology |

## 2-1. Policy & Institutional KPIs

| Milestone | Target | Timeline |
| --- | --- | --- |
| Recycling Industrial Parks | Legal framework + pilot parks established | By 2027 |
| HS Codes for Env. Goods | Environmental goods HS codes issued | 2025 (immediate) |
| Tax Policy Reform | Tax incentives for environmental goods + tech transfer | 2025–2026 |
| Government Decree | Decree specifically regulating environmental industry | By 2030 |
| National Env. Industry Center | Established and operational | By 2028 |
| National Statistics | Environmental industry added to national stat system | 2025–2026 |
| Foreign Investment | FDI attracted into environmental technology sector | Ongoing |

# 3. Six Major Task Areas & Implementation Status

## Completing Policy & Institutional Framework

| Lead Ministry | MOIT + MONRE + MOF + MOST |
| --- | --- |
| Implementation Status | 🟡 In Progress HS code issuance initiated; tax policy review underway; Decree drafting not yet started |

### Sub-Tasks

▪ Review and update legal framework for environmental industry development

▪ Develop and publish standards/technical regulations for environmental industry goods

▪ Amend tax policy to favor environmental goods and promote technology transfer

▪ Add environmental industry statistics to national statistical system

▪ Issue HS codes for environmental goods in harmonized tariff schedule

▪ Enact incentive policies for recycling industrial parks and clusters

▪ Support enterprises receiving technology transfer, purchasing patents/software

▪ Review catalogue of specific technologies (Decision 980/QD-TTg): WTE, wastewater treatment, recycled construction materials, RE waste recycling, monitoring systems, biodegradable plastics

▪ Draft Government Decree on environmental industry development

## Developing Environmental Industry Goods Market

| Lead Ministry | MOIT |
| --- | --- |
| Implementation Status | 🟡 Early Stage Government procurement mechanisms being designed; incubator network concept phase |

### Sub-Tasks

▪ Stimulate market demand through government procurement orders and direct contracting for domestic enterprises

▪ Develop supply capacity of environmental technology enterprises

▪ Support SMEs + establish environmental industry incubator network in industrial parks, hi-tech zones, and training institutions

▪ Eco-labeling for environmental industry products

▪ Trade promotion and investment attraction activities

▪ Develop environmental industry enterprises under state conglomerates (PETROVIETNAM, VINACHEM, VINACOMIN, VEAM, VINAINCON)

▪ Promote public-private partnerships in R&D and production

▪ Establish National Environmental Industry Centers (national-level production, tech transfer, innovation hubs)

## R&D, Innovation & Digital Transformation

| Lead Ministry | MOIT + MOST |
| --- | --- |
| Implementation Status | 🟡 In Progress Decision 980 catalogue review underway; RE waste recycling technology R&D initiated |

### Sub-Tasks

▪ Master and develop technologies in the Decision 980 catalogue: WTE, wastewater treatment, recycling, biodegradable plastics, green materials

▪ Disseminate advanced production processes and pollution reduction technologies

▪ Research, prototype, and transfer advanced environmental technologies

▪ Support enterprises receiving technology transfer, purchasing patents/software, hiring experts

▪ International cooperation in training, research, and technology transfer

▪ RE waste treatment technology (solar panel recycling, wind turbine blade recycling)

▪ Apply CAD/CAM in equipment manufacturing

▪ Develop mechatronic equipment and automated control systems for environmental industry

▪ Biosensor products for environmental monitoring

▪ Support adoption of sustainable business models, energy efficiency, circular economy

## Training & Human Resource Development

| Lead Ministry | MOIT + MOET |
| --- | --- |
| Implementation Status | ⚪ Planning Curriculum development not yet reported |

### Sub-Tasks

▪ Build database on human resource needs and quality for environmental industry

▪ Develop training programs and courses for state managers, enterprise managers, and technical workers

▪ Design HR development curriculum for environmental industry

## Environmental Industry Information Portal

| Lead Ministry | MOIT |
| --- | --- |
| Implementation Status | 🟡 In Progress Environmental industry portal development announced by MOIT (Oct 2025) |

### Sub-Tasks

▪ Build and update enterprise database of environmental industry goods

▪ Develop web portal for information storage, retrieval, and updates on environmental industry

▪ Invest in maintaining and upgrading portal infrastructure

▪ Annual data updates on environmental industry development

## Communications & Awareness

| Lead Ministry | MOIT + all ministries |
| --- | --- |
| Implementation Status | 🟢 Active MOIT held environmental industry development conference (Oct 2025); media campaigns launched |

### Sub-Tasks

▪ Public communication campaigns on environmental industry via mass media

▪ Competitions and awareness programs on environmental industry

▪ International information exchange and best practice sharing

▪ Awards and recognition for contributions to environmental industry development

▪ Support enterprises participating in Vietnam National Brand program

# 4. Key Technology Sectors — Market Potential

## Manufacturing of wastewater treatment equipment, systems, and chemicals

| 2030 Target | Meet 70–80% of domestic market + export capability |
| --- | --- |
| Key Products / Equipment | WWTP modules, MBR systems, SBR systems, UV disinfection units, pump & pipe systems, sludge treatment equipment, biological treatment chemicals |
| Current Gap | High import dependency from Korea, Japan, EU for advanced treatment systems |

## Air pollution control equipment for industrial sources

| 2030 Target | Meet 60–70% of domestic market |
| --- | --- |
| Key Products / Equipment | electrostatic precipitators, bag filters, scrubbers, DeNOx/DeSOx systems, continuous emission monitoring (CEMS) |
| Current Gap | Advanced systems almost entirely imported; basic equipment locally made |

## Collection, sorting, recycling, and treatment equipment

| 2030 Target | 50–60% collection/transport needs; 60–70% sorting/recycling needs |
| --- | --- |
| Key Products / Equipment | collection vehicles, sorting lines, incinerators, composting systems, hazardous waste treatment units, recycling machinery |
| Current Gap | Incineration and hazardous waste treatment relies heavily on imported technology |

## Environmental measurement and monitoring equipment

| 2030 Target | Meet 20% of domestic demand |
| --- | --- |
| Key Products / Equipment | air quality sensors, water quality analyzers, IoT monitoring networks, automated monitoring stations (AMS), portable analyzers |
| Current Gap | Almost entirely import-dependent; some local assembly |

## Technology and equipment for energy production from waste

| 2030 Target | Develop domestic WTE technology capability |
| --- | --- |
| Key Products / Equipment | WTE boilers, biogas digesters, landfill gas recovery systems, RDF (refuse-derived fuel) production lines |
| Current Gap | Large-scale WTE plants use imported technology (China, Europe) |

## Establishment of dedicated recycling clusters as anchor institutions

| 2030 Target | Legal framework + at least pilot recycling industrial parks established |
| --- | --- |
| Current Gap | No formal recycling industrial parks exist; concept in development |
| Concept | Eco-industrial parks where environmental technology companies co-locate for synergies |

# 5. Province Activity — Recent News (2026)

ℹ️ Note: The articles below are collected from news sources and represent recent activities related to the D1894 program areas. They serve as progress indicators, NOT as official program reports. Some articles may cover related environmental industry activities without explicitly referencing Decision 1894.

## 📍 Hanoi

Role: National R&D hub; university-industry linkage; government procurement market

Opportunities: National Environmental Industry Center candidate; monitoring equipment R&D; university partnerships

ℹ️ No recent news collected for this province.

## 📍 Ho Chi Minh City

Role: Largest industrial market; private sector leadership; export gateway

Opportunities: Largest demand center for env. technology; WTE technology hub; recycling industrial park pilot

ℹ️ No recent news collected for this province.

## 📍 Binh Duong

Role: Industrial park concentration; eco-industrial park development

Opportunities: Eco-industrial park conversion; industrial wastewater treatment tech demand

ℹ️ No recent news collected for this province.

## 📍 Dong Nai

Role: Major industrial province; large wastewater/solid waste market

Opportunities: Industrial waste treatment technology demand; hazardous waste management

ℹ️ No recent news collected for this province.

## 📍 Hai Phong

Role: Northern industrial hub; port logistics

Opportunities: Industrial env. technology demand; export platform for env. equipment

ℹ️ No recent news collected for this province.

## 📍 Da Nang

Role: Central region hub; smart city + environmental technology pilot

Opportunities: Smart environmental monitoring pilot; SME environmental tech incubator

ℹ️ No recent news collected for this province.

## 📍 Can Tho

Role: Mekong Delta environmental challenge hotspot

Opportunities: Wastewater/solid waste technology demand; agricultural waste treatment

ℹ️ No recent news collected for this province.

## 📍 National

### Recent News (1 articles)

[1] Việt Nam's shift to green growth | Vietnam Today - YouTube

📅 2026-02-22  |  📰

🇰🇷 베트남은 COP26에서 2050년까지 넷제로 달성을 선언하며 경제 구조를 녹색 성장으로 전환하고 있습니다. VN-EV-2030 계획의 일환으로 폐기물 관리 인프라를 개선하고 지속 가능한 고체 폐기물 처리 솔루션을 구축하는 데 집중하고 있습니다.

🇺🇸 Vietnam is transitioning its economic trajectory toward green growth following its COP26 commitment to reach net-zero emissions by 2050. Under the VN-EV-2030 framework, the country is prioritizing inf

https://www.youtube.com/watch?v=mEq68PU4JbM

# 6. Ministry Responsibilities & Coordination

| Ministry / Agency | Responsibility |
| --- | --- |
| MOIT | Lead coordinator; policy framework; market development; enterprise development; national centers; annual reporting |
| MONRE | Environmental standards; monitoring network; EPR implementation; international environmental agreements |
| MOF | Budget allocation; tax policy for environmental goods; green finance framework |
| MOST | R&D funding; technology transfer; innovation programs; standards development |
| MOC | Construction standards for environmental facilities; building code integration |
| MARD | Agricultural/rural environmental technology needs; water resource protection |
| Provincial Peoples Committees | Implement at province level; allocate land for recycling industrial parks; support local enterprises; annual provincial progress reporting to MOIT |

## 6-1. Implementation Timeline

📅 2025 immediate: Issue HS codes for environmental goods  ·  Begin policy framework review  ·  Launch environmental industry information portal

📅 2025 2026: Amend tax policies for environmental goods  ·  Launch SME incubator network  ·  Begin national environmental industry statistics compilation  ·  Initiate recycling industrial park pilot sites

📅 2027 2028: Draft Government Decree on environmental industry  ·  Establish National Environmental Industry Center  ·  Scale up domestic equipment manufacturing

📅 2029 2030: Achieve KPI targets for domestic market share  ·  Export of advantageous environmental technologies  ·  Full policy framework in place

# 7. Risk Assessment & Korean Business Opportunity

| Category | Analysis |
| --- | --- |
| 🚨 Key Risks | 1. Implementation speed uncertain — policy framework still being drafted 2. Private sector capacity to deliver domestic technology remains low 3. Competing priorities: infrastructure construction demand vs. technology industry development 4. Limited access to green credit for SME environmental tech companies 5. Foreign technology still dominant — localization targets ambitious |
| 💡 Korean Company Opportunities | HIGH PRIORITY: ▪ Technology Transfer Partnership: Korean env. tech companies can transfer technology to Vietnamese partners → preferred vendor status + tax incentives ▪ Joint Venture in Environmental Equipment: Local manufacturing of Korean-designed WWTP modules, monitoring systems ▪ Environmental Industry Incubator: Korean companies can co-develop SME incubators (Korea has proven models via KOICA/KOTRA) MEDIUM PRIORITY: ▪ Recycling Industrial Park Development: Korea LH Corporation already active (Hung Yen Smart City) — D1894 recycling park framework creates new entry points ▪ Monitoring Equipment Manufacturing: Korean sensors/analyzers → partner with local assembly to meet 20% domestic target ▪ WTE Technology: Korean WTE companies (KEPCO, Samsung C&T) can position for technology transfer SPECIFIC ENTRY POINTS: ▪ Decision 980 catalogue review → submit Korean technologies for inclusion ▪ National Environmental Industry Center tender when announced ▪ Government procurement programs → preferred domestic partner status through JV |
| 📈 Market Outlook | 2025–2026: Policy framework phase — limited immediate market but critical for positioning 2026–2028: Market formation — procurement programs begin; incubators launch; early technology transfer deals 2028–2030: Scale-up phase — domestic production ramps; export ambitions materialize Total environmental technology market size: est. $2–3B by 2030 Technology transfer deals: expected $500M+ over program period MOIT actively seeking international partners — Korean companies have strong positioning via existing government relationships |
| ⚠️ Strategic Note | D1894 is a TECHNOLOGY INDUSTRY program. Business strategies should focus on: 1. PARTNERSHIP MODEL (not just export) — Vietnamese companies need technology, not finished goods 2. EARLY POSITIONING — policy framework phase is the best time to engage 3. MOIT is the primary engagement target (not MONRE) — this is an industry program 4. KOTRA/KOICA/EXIM Bank programs can support Korean company entry |

# 8. Appendix — All Relevant Articles (38 articles, filter-passed)

Total matched: 448 | Relevance-filtered: 38 | Excluded as infrastructure construction news (not D1894-specific): 410
Full article history available in Database Excel — 'D1894' sheet.

| No | Date | Title (EN/KO) | Source | Province |
| --- | --- | --- | --- | --- |
| 1 | 2026-02-22 | Việt Nam's shift to green growth ¦ Vietnam Today - YouTube |  | National / Unspecifi |
| 2 | 2025-12-15 | Vietnam inaugurates USD1.4 billion LNG power plants in energ |  | National / Unspecifi |
| 3 | 2025-11-26 | Việt Nam outlines new plan to cut waste, protect coastal ... |  | Hanoi |
| 4 | 2025-09-05 | Vietnam's green horizon: A 2025-2030 plan for ... |  | National / Unspecifi |
| 5 | 2025-01-08 | Vietnam's 2050 Net-Zero Target Represents a $2.4 Trillion Op |  | National / Unspecifi |
| 6 | 2024-11-18 | Switzerland provides US$3.3 million to promote Việt Nam's ci | Vietnam News | Vietnam |
| 7 | 2024-11-10 | Circular economy promoted via waste sorting, recycling at Gr | The Youth | Vietnam |
| 8 | 2024-10-22 | Vietnam promoting circular economy through waste, packaging | Vnanet | Vietnam |
| 9 | 2024-10-15 | SABECO collaborates to advance circular economy | Vietnam News | Vietnam |
| 10 | 2024-08-25 | Vietnam promotes circular economy in waste recycling | Vietnam Plus | Vietnam |
| 11 | 2024-08-06 | Da Nang calls for investment to innovate waste treatment tec | Labour news | Da Nang |
| 12 | 2024-07-15 | Transitioning from a linear economy to a circular economy to | VEN | Vietnam |
| 13 | 2024-06-16 | Promoting green lifestyle and circular economy | Da Nang News | Da Nang |
| 14 | 2024-05-26 | Developing waste treatment technology turns Tay Ninh into a | Environment & urban | Tay Ninh |
| 15 | 2024-04-04 | EPR a powerful tool to reduce pollution and boost recycling | Vietnam News | Vietnam |
| 16 | 2024-03-21 | Movement underway to promote EPR | Vietnam Investment R | Vietnam |
| 17 | 2024-01-26 | Important progress in EPR implementation | VEN | Vietnam |
| 18 | 2023-12-16 | Vietnam ready to implement EPR regulations | Sai Gon News | Vietnam |
| 19 | 2023-10-18 | Dutch enterprise use WtE technology | Ba Ria Vung Tau News | Ba Ria Vung Tau |
| 20 | 2023-10-05 | Biodegradable organic solid waste materials for energy recov | Sai Gon News | Ho Chi Minh City |
| 21 | 2023-03-08 | Ministry plans to increase environmental protection tax on n | Vietnam Plus | Vietnam |
| 22 | 2022-11-26 | Project on plastic waste management based on circular econom | Vietnam News | Ho Chi Minh City |
| 23 | 2022-08-29 | Outdated waste treatment technology in Vietnam | Investment & Finance | Vietnam |
| 24 | 2022-08-09 | No ideal waste treatment technology for Vietnam yet | Vietnam Express | Vietnam |
| 25 | 2022-07-06 | Collective efforts for Việt Nam to shift to circular economy | Vietnam News | Vietnam |
| 26 | 2022-06-29 | Da Nang to build sustainable circular economy for plastic wa | Danang News | Da Nang |
| 27 | 2022-06-07 | Plastic waste reduction via a circular economy | Vietnam Investment R | Vietnam |
| 28 | 2022-02-24 | Vietnam-WEF partnership helps reduce plastic waste, develop | Vietnamplus | Vietnam |
| 29 | 2021-09-24 | RMIT University to represent Viet Nam at ASEAN Data Science | Da Nang news | Vietnam |
| 30 | 2021-09-16 | EPR to promite recycling businesses to form circular ecosyst | Intellasia | Vietnam |
| 31 | 2021-06-03 | Circular economy helps Vietnam tackle climate change: Minist | Hanoi Times | Vietnam |
| 32 | 2021-01-08 | Recycled packaging: A key part of circular economy | The Saigon times | Vietnam |
| 33 | 2020-11-01 | Danang Circular Economy Hub to officially debut on 11 Nov | Da Nang news | Da Nang |
| 34 | 2020-08-03 | Which opportunity for the waste treatment technology and was | MOIT | Vietnam |
| 35 | 1900-01-01 | Vietnam accelerates battle against plastic waste |  | National / Unspecifi |
| 36 | 1900-01-01 | The Vietnam Water and Environment Association ... - YouTube |  | Hanoi |
| 37 | 1900-01-01 | Viet Nam - Policies & action ¦ Climate Action Tracker |  | National / Unspecifi |
| 38 | 1900-01-01 | Current status of industrial waste management in Vietnam |  | National / Unspecifi |