Signed by: Ministry of Industry and Trade

Agency : Ministry of Industry and Trade

MINISTRY OF INDUSTRY AND TRADE, SOCIALIST REPUBLIC 	Signing time: 16.12.2025 11:54:42 +07:00

Independence - Self-reliance - Happiness

No.: 	/QD-BCT 	Hanoi, December 2025

DECISION

Issuance of the Action Plan of the Ministry of Industry and Trade to implement Decision 
No. 1894/QD-TTg dated September 4, 2025 of the Prime Minister approving 
the Program for the Development of Vietnam's Environmental Industry Sector 
for the period 2025 - 2030

MINISTER OF INDUSTRY AND TRADE

Based on Decree No. 40/2025/ND-CP dated February 26, 2025 of the Government stipulating the functions, tasks, powers and organizational structure of the Ministry of Industry and Trade;

Based on the Law on Environmental Protection dated November 17, 2020;

Based on Decision No. 1894/QD-TTg dated September 4, 2025 of the Prime Minister approving the Program for the Development of Vietnam's Environmental Industry in the period 2025 - 2030;

As requested by the Director of the Department of Industrial Safety and Environmental Engineering.

DECISION

Article 1. This Decision approves the Action Plan of the Ministry of Industry and Trade to implement Decision No. 1894/QD-TTg dated September 4, 2025 of the Prime Minister approving the Program for the Development of Vietnam's Environmental Industry Sector for the period 2025 - 2030 with the following main contents:

- Purpose, requirements

- Purpose

- To implement in a unified, synchronized, and effective manner the tasks and solutions assigned by the Prime Minister in Decision No. 1894/QD-TTg dated September 4, 2025 , approving the Program for the Development of Vietnam's Environmental Industry Sector for the period 2025-2030.

- Mobilize the practical and proactive participation of agencies, units, civil servants, and employees of the Ministry of Industry and Trade in activities related to the development of the environmental industry.

- Specifically, the contents will be clarified, and based on that, units within the Ministry of Industry and Trade will be assigned to effectively implement the Prime Minister's Decision.

and mobilize close coordination among Departments of Industry and Trade, corporations, and businesses in developing the environmental industry.

- Request

- The development and implementation of the Action Plan must be widely carried out in agencies, units, and mass organizations of the Ministry of Industry and Trade with diverse, practical, and effective content and forms.

- Based on the existing shortcomings, limitations, difficulties, and obstacles in the development of the environmental industry, specific tasks are proposed to address these issues and support businesses in effectively implementing the requirements of the Prime Minister's Decision.

- The plan involves both effectively implementing the Action Plan and simultaneously promoting and disseminating information about the Ministry of Industry and Trade's efforts in developing the environmental industry.

- Action plan

The main tasks and assigned focal points for coordinating the implementation of the Ministry of Industry and Trade's Action Plan to implement Decision No. 1894/QD-TTg dated September 4, 2025, of the Prime Minister approving the Program for the Development of Vietnam's Environmental Industry Sector for the period 2025-2030 are detailed in Appendix 1 and Appendix 2 attached to this Decision.

- Funding for implementation

Funding for the implementation of the Plan will be mobilized from the following sources: Central and local budgets, state budget funds for environmental protection, economic development, and science and technology; enterprise resources, loans from credit institutions, and environmental protection funds, in accordance with the financial resources approved by the Prime Minister in Decision No. 1894/QD-TTg dated September 4, 2025, approving the Program for the Development of Vietnam's Environmental Industry in the period 2025-2030.

- Implementation

- The Department of Industrial Safety and Environmental Engineering is the lead agency responsible for coordinating with relevant units to implement the Plan; it acts as the focal point for monitoring and coordinating with units under the Ministry to implement the Plan; it compiles annual reports on the implementation status and submits them to the Ministry of Industry and Trade leadership; and it periodically conducts preliminary and final reviews to assess the results and effectiveness of the Plan's implementation and reports to the Prime Minister.

- Based on this Plan and their respective functions, duties, and powers, the heads of agencies and units under the Ministry of Industry and Trade shall organize the implementation of the tasks of the Plan as assigned in Appendix 1 and Appendix 2 of this Decision, integrating...

Integrate the content and activities for developing the environmental industry into the unit's annual work program and plan; annually report on the implementation status to the coordinating unit for consolidation and reporting to the Ministry of Industry and Trade leadership.

- The Departments of Industry and Trade of provinces and cities, based on the specific characteristics of their localities, should proactively develop plans to implement the Program and proactively propose to local leaders the allocation of local budgets and other legally mobilized resources for its implementation.

- Corporations and enterprises under the Ministry of Construction shall develop their own plans and organize the implementation of related tasks and solutions to carry out the contents of the Ministry of Industry and Trade's Action Plan, contributing to the successful implementation of the Vietnam Environmental Industry Development Program for the period 2025 - 2030.

- The Vietnam Environmental Industry Association collaborates with units of the Ministry of Industry and Trade to develop the environmental industry in accordance with its assigned functions and tasks.

- During the implementation process, if it is necessary to supplement, adjust, or modify the contents of the Action Plan, the heads of agencies and units shall report to the Ministry of Industry and Trade through the focal unit for compilation and reporting to the Minister for consideration and decision.

Article 2. This Decision shall take effect from the date of signing.

Article 3. Chief of the Ministry's Office, Heads of agencies and units under the Ministry;

Directors of the Departments of Industry and Trade of provinces and cities; Chairpersons of the Board of Members, Chairpersons of the Board of Directors, and General Directors of corporations and enterprises.

The Ministry responsible for implementing this Decision./.

Truong Thanh Hoài

Recipient:

- As per Article 3;

- Prime Minister (for information/reporting);

- Minister (for information/reporting);

- Government Office;

- Ministries: Agriculture and Environment; Construction; Science and Technology; Finance;

- Departments of Industry and Trade of provinces and cities;

- Corporations under the Ministry;

- Save: VT, ATMT.

APPENDIX 1

ASSIGNMENT OF TASKS TO UNITS IMPLEMENTING THE ACTION PLAN 
OF THE MINISTRY OF INDUSTRY AND TRADE TO IMPLEMENT DECISION NO. 1894/QD-TTg DATED SEPTEMBER 4, 
2025 OF THE PRIME MINISTER APPROVING THE PROGRAM FOR THE 
DEVELOPMENT OF THE ENVIRONMENTAL INDUSTRY FOR THE PERIOD 2025-2030 
(Attached to Decision No. 3637 /QD-BCT dated December 2025 of the 
Minister of Industry and Trade)

- Department of Industrial Safety and Environmental Engineering (Department of Safety and Environment)

- As the lead agency, we will coordinate with relevant units to organize and implement the Action Plan.

- Providing guidance to agencies, organizations, and individuals on developing annual plans and implementing activities within the scope of management of the Ministry of Industry and Trade;

- The organization reviews the list, content, and budget of annual tasks proposed by relevant agencies and organizations based on the Program approved by the Prime Minister, and submits them to the Ministry's leadership for approval;

- Prepare a budget estimate for the implementation of the Program and submit it to the Ministry's leadership for inclusion in the Ministry of Industry and Trade's annual budget.

- Develop regulations for managing and implementing tasks under the Program.

- Responsible for building, updating, and managing the database and website on the environmental industry.

- As the focal point of the Ministry of Industry and Trade, it collaborates with domestic and foreign organizations and individuals to attract capital and resources for the development of the environmental industry.

- Chairing and coordinating with the Department of Standards, Metrology and Quality Control and the Department of Industry to implement priority activities on labeling for environmental industrial products and goods;

- Department of Planning, Finance and Business Management (Department of Planning and Finance)

+ Ensure budget balance for activities implementing the Environmental Industry Development Program; act as the focal point to coordinate with the Ministry of Finance to allocate funding for the Program; develop statistical indicators for the environmental industry to be added to the national statistical system.

+ Coordinate with the Department of Environmental Safety to support participating units in carrying out tasks under the Program in preparing budget estimates according to current financial regulations; and finalize accounts for tasks.

+ Support and connect relevant businesses and organizations to access green finance in order to develop the environmental industry.

+ The study proposes the development of several environmental industrial enterprises under the following corporations: VEAM, VINAINCON...

- Department of Innovation, Green Innovation and Industrial Promotion (Department of Industrial Promotion)

+ Preside over and coordinate the implementation of science and technology tasks, innovation, and digital transformation to serve the development of the environmental industry.

+ Coordinate with the Department of Environmental Safety and Technology and the Department of Industry to establish a network of environmental industry business incubators in industrial clusters and high-tech zones; research and develop national-level environmental industry centers.

+ Organize the review of draft national standards for environmental industry products.

- Department of Industry (Department of CN): Responsible for leading and coordinating the implementation of tasks to support environmental industrial enterprises in improving their capacity to supply equipment, technology, and environmental industrial products.

- Trade Promotion Agency ( TPA): Leads and supports environmental industry enterprises in participating in the National Trade Promotion Program; the Vietnam National Brand Program; and regular domestic and international trade promotion activities.

- Department of Personnel and Organization (Department of TCCB):

+ Chair and coordinate with the Department of Environmental Safety to develop training programs and organize training courses to improve the skills of state management officials in the environmental industry, and management and technical workers in environmental industry enterprises; Develop human resource training programs to serve the development of the environmental industry.

+ Coordinate with the Vietnam Environmental Industry Association (VIA) and businesses to organize events to honor and reward outstanding examples of environmental industry development.

- The Ministry's media outlets

+ Organize publicity campaigns

+ Develop communication programs and competitions to learn about the environmental industry; disseminate and replicate experiences and research results...

APPENDIX 2

CONTENTS OF THE ACTIVITIES IN THE ACTION PLAN OF THE MINISTRY OF INDUSTRY AND TRADE TO IMPLEMENT 
DECISION NO. 1894/QD-TTG DATED SEPTEMBER 4, 2025 OF THE PRIME MINISTER APPROVING THE PROGRAM FOR THE 
DEVELOPMENT OF THE ENVIRONMENTAL INDUSTRY FOR THE PERIOD 2025 - 2030 
(Attached to Decision No. 363Y/QD-BCT dated December 1, 2025)

| TT | Task Name | Organizing unit | Coordinating unit | Time |
| --- | --- | --- | --- | --- |
| L. Improve the policy and institutional framework for the development of the environmental industry. |  |  |  |  |
| 1 | Drafting a Government Decree on the development of the environmental industry. | Department of Environmental Safety | Legal Affairs Department | 2026 - 2030 |
| 2 | Develop a number of technical standards and regulations for goods in the environmental industry. | Department of Environmental Safety | Customs Department, Vietnam Association of Mechanical Engineers & Members | 2026 - 2030 |
| 3 | Review the specific list of technologies, equipment, and products in the environmental industry to submit to the Prime Minister for adjustment and supplementation of Decision No. 980/QD-TTg dated August 22, 2023. | Department of Environmental Safety | Relevant Departments and Bureaus, Department of Industry and Trade | 2026 - 2028 |
| 4 | Further research is being conducted to add technologies and equipment for waste treatment to the list of key mechanical products. | Department of Industry | Department of Environmental Safety, Legal Affairs Division | 2026 - 2028 |
| 5 | Research and supplement the national statistical indicator system with statistical indicators for the environmental industry. | Planning and Finance Department | Department of Environmental Safety, and related Departments and Divisions | 2026 - 2030 |
| 6 | Research on developing regulations for identifying codes for environmental goods within the Harmonized System of Tariffs (HS code) | Department of Environmental Safety | Relevant Departments and Divisions, Vietnam Association of Environmental Technology and its members | 2025 - 2028 |
| II. Development of the market for environmental industrial goods |  |  |  |  |

| 1 | Research, formation and development of several environmental industrial enterprises under the management of the Ministry of Industry and Trade, such as VINAINCON, VEAM... | Planning and Finance Department | Department of Safety and Environment, Department of Industry, Department of Customs; General Corporations under the Ministry: VINAINCON, VE AM... | 2026 - 2030 |
| --- | --- | --- | --- | --- |
| 2 | Research into establishing national-level environmental industrial centers, focusing on production capacity, technology transfer, and innovation. | Securities and Exchange Commission | Department of Food Safety and Hygiene, Department of Industry, Department of Domestic Market Development | 2026 - 2030 |
| 3 | Organizing domestic and international trade fairs and exhibitions for technologies, equipment, and products of the environmental industry aims to promote trade and advertise Vietnamese brands in the environmental industry sector. | Trade Promotion Agency | Department of Environmental Safety, Department of Industry, Vietnam Association of Environmental Industry and its members | Annual |
| 4 | Implement priority activities regarding labeling for environmental industrial products and goods. | Department of Environmental Safety | Department of Securities and Exchange, Department of Industry, Department of Domestic Market Development | 2028 - 2030 |
| 5 | Supporting small and medium-sized enterprises, combined with establishing a network of environmental industry business incubators in industrial parks, clusters, high-tech zones, and key training institutions. | Securities and Exchange Commission | Department of Environmental Safety, Department of Industry, Department of Organization and Personnel, Universities and Colleges under the Ministry of Industry and Trade | 2026 - 2030 |
| III. Developing science and technology, innovation, and digital transformation to serve the development of the environmental industry. |  |  |  |  |
| 1 | Promote scientific and technological activities to master and develop technologies, equipment, and products belonging to the specific list of technologies, equipment, and products in the environmental industry issued with Decision No. 980/QD-TTg dated August 22, 2023, serving waste treatment and environmental protection to meet domestic and export needs. | Securities and Exchange Commission | Department of Environmental Safety, Department of Industry | 2025 - 2030 |

| 2 | Introducing and disseminating some technological processes for producing products and preparations for pollution reduction, waste treatment, environmental remediation, and technical requirements for goods in the environmental industry. | Department of Environmental Safety | Department of Customs, Department of Industry, Vietnam Association of Industrial and Commercial Enterprises and its members | 2025 - 2030 |
| --- | --- | --- | --- | --- |
| 3 | Promoting environmental industry businesses to adopt energy-saving and efficient energy use models; sustainable production and consumption models; and circular economy models. | Securities and Exchange Commission | Department of Environmental Safety, Department of Industry, Vietnam Association of Environmental Industry & its members | 2026 - 2030 |
| 4 | Providing support for businesses to adopt management systems based on international standards, and management systems that meet the requirements of global production chains in business management and production management. | Planning and Finance Department | Department of Environmental Safety, Department of Industry, Department of Customs; Vietnam Association of Environmental Technology | 2026 - 2030 |
| 5 | Applying computer-aided design and manufacturing (CAD/CAM) technologies in equipment manufacturing. | Securities and Exchange Commission | Department of Industry, Vietnam Association of Industrial and Commercial Enterprises & its members | 2026 - 2030 |
| 6 | Applying mechatronic devices and modern, intelligent automatic control systems to biotechnology production lines and equipment serving the environmental industry. | Securities and Exchange Commission | Department of Industry, Vietnam Association of Industrial and Commercial Enterprises & its members | 2026 - 2030 |
| IV. Training, capacity building, and human resource development for the environmental industry. |  |  |  |  |
| 1 | Establishing a database on human resource needs and quality to serve the development of the environmental industry. | Department of Environmental Safety | Department of Personnel and Organization, Vietnam Association of Industrial and Commercial Enterprises and its members | 2026-2028 |
| 2 | Develop training programs and organize advanced training courses for state management officials in the environmental industry and management staff. | Personnel Department | Department of Environmental Safety, Vietnam Association of Environmental Technology and its members; technical universities | 2026-2030 |

|  | and technical workers at environmental industrial enterprises |  | technical college, research institute of the Ministry of Industry and Trade |  |
| --- | --- | --- | --- | --- |
| 3 | Develop training programs for human resources to serve the development of the environmental industry. | Department of Environmental Safety | Department of Personnel and Organization, Vietnam Association of Industrial and Commercial Enterprises and its members | 2026-2028 |
| 4 | Integrating human resource training content for the environmental industry into the technical university, college, and university programs of the Ministry of Industry and Trade. | Personnel Department | Vietnam Association of Technology and Engineering and its members; technical universities, colleges, and universities under the Ministry of Industry and Trade. | 2026-2028 |
| V. Building and operating a website on environmental industry information |  |  |  |  |
| 1 | Develop and update a comprehensive business database of goods in various sectors of the environmental industry. | Department of Environmental Safety | Department of Industry, Vietnam Association of Industrial and Commercial Enterprises and its members | 2026 - 2028 |
| 2 | Develop a website that meets the needs for storing, retrieving, and updating information about the environmental industry. | Department of Environmental Safety | E-commerce Department, Vietnam Association of Information Technology and Communications, and its members | 2027 - 2030 |
| 3 | Annual updates on environmental industry development data. | Department of Environmental Safety | Department of Industry, Vietnam Association of Industrial and Commercial Enterprises and its members | Annual |
| VI. Strengthening communication and dissemination efforts regarding the environmental industry. |  |  |  |  |
| 1 | Organize public awareness campaigns on environmental industry through mass media. | The Ministry's media outlets (Industry and Trade Newspaper, Industry and Trade Magazine, Industry and Trade Television) | Department of Environmental Safety, Ministry Office, Vietnam Association of Environmental Technology | Annual |

|  |  | Love) |  |  |
| --- | --- | --- | --- | --- |
| 2 | Develop and organize communication programs and competitions to learn about the environmental industry; disseminate and replicate the results and research on technologies, equipment, and products of the environmental industry. | The Ministry's media outlets (Industry and Trade Newspaper, Industry and Trade Magazine, Industry and Trade Television) | Department of Environmental Safety, Ministry Office, Vietnam Association of Environmental Technology | Annual |
| 3 | Strengthen information exchange and international cooperation, and disseminate experiences from successful environmental industry development models both domestically and internationally through specialized newspapers, magazines, and mass media. | The Ministry's media outlets (Industry and Trade Newspaper, Industry and Trade Magazine, Industry and Trade Television) | Department of Environmental Safety, Ministry Office, Vietnam Association of Environmental Workers | Annual |
| 4 | Honoring and rewarding collectives and individuals with outstanding achievements in the development of the environmental industry. | Association ​ CNMTVN | Department of Personnel and Organization, Department of Environmental Safety, Department of Industry, and related organizations and individuals. | Annual |
| 5 | Encourage and support businesses to participate in activities of the National Trade Promotion Program, the Vietnam National Brand Program, and other regular trade promotion activities. | Trade Promotion Agency | The Department of Environmental Safety, the Vietnam Association of Environmental Workers and its members, VCCI, and relevant associations and organizations. | Annual |